## Slide 1
CLSA – Executive Summary
November 2018

## Slide 2: EXECUTIVE SUMMARY
Client Preference Editor
Pace
Progress
Data Editor
Pace
Progress
Reports Migration
Pace
Progress
Under UAT
On Track
PR Pending
95%
90%
0%
As we gear up to build key solutions, we have focused on doing it the right way through structure, quality, robust processes, and high commitment
CLSA – OVERALL PROJECT STATUS
Development Done. Application under UAT.
Change Requests Pending
Last Sprint in progress.
No major roadblocks till date
Risks
NIL
Insights
Risks
NIL
Insights
Risks
NIL
Insights
PR Pending approval

## Slide 3: Project 1: Client Preference Editor
 | DETAILS | DATE | STATUS | COMMENTS
Sprint 1 | Requirement, Wireframes & Screen Design | 03 Sept - 12 Sept |  | Pending Sign Off from CLSA
Sprint 2 | Technical Architecture and Specification | 14 Sept - 25 Sept |  | Sankey team delivered as per schedule
Sprint 3 | Programming - Create and Update Preferences | 26 Sept - 09 Oct |  | Sankey team delivered as per schedule
Sprint 4 | Programming - Client Listing & History | 10 Oct - 19 Oct |  | Sankey team delivered as per schedule
Sprint 5 | Programming - Maker-Checker Client Level | 22 Oct - 02 Nov |  | Sankey team delivered as per schedule
Sprint 6 | Programming - Checker Static Level | 03 Nov – 16 Nov |  | Sankey team delivered as per schedule
Sprint 7 | Data . Migration and Integration Testing | 19 Nov - 03 Dec |  | Integration Done. UAT in progress
 | Staging Deployment and UAT | 04 Dec - 20 Dec | WIP | 
 | Production Release | TBD |  | 

## Slide 4: Project 2: Data Editor
 | DETAILS | DATE | STATUS | COMMENTS
Sprint 1 | Requirement, Wireframes & SRS | 19 Sept - 04 Oct |  | Sign-off received
Sprint 2 | Technical Architecture Document, Screen Design and Test Case Scenarios | 05 Oct - 19 Oct |  | Sign-off received
Sprint 3 | Programming – Authentication & Authorization, Namespace and Entities Listing, Basic Automated Unit Test Cases | 22 Oct - 05 Nov |  | Sprint 3 delivered
Sprint 4 | Programming – Entities Data Listing, Filtering Entity Data, Basic Automated Unit Test Cases | 06 Nov - 20 Nov |  | Sprint 4 delivered
Sprint 5 | Programming – Filtering Entity Data, Freeze Record, Delete Record, Basic Automated Unit Test Cases | 21 Nov - 05 Dec |  | Sprint 5 delivered
Sprint 6 | Programming – Update Record, Add Record, Record History, Basic Automated Unit Test Cases, Internal Testing | 06 Dec - 20 Dec | WIP | 
 | Staging Deployment and UAT | TBD |  | 
 | Production Release | TBD |  | 

## Slide 5: Overall Value Additions / Next Steps
Business Users
Design
Directional Inputs
Architecture
Demo Prototyping and Video
Ahead-of-time experience to business users, using Adobe XD, to create interactive demo video, as they could see the prototypes in action
Blockchain
CLSA Revenue Generation - Recommendation Engine
Use cases / trades where created records needs to be immutable and secure in distributed environment, using blockchain DAPP architecture
Arming brokers with better client preference insights, using analytical engine for CPE will lead to higher quality and volume of transactions. Team presented the analytical model for CLSA revenue generation
Searchable Encrypted Database
Challenge to allow range and equality search on an encrypted database. Team suggested use of Elasticsearch on premise or on cloud, to index data and query encrypted text
Reactive Programming
Reactive programming is programming with asynchronous data streams.
Team introduced ngRx, uni-directional state management pattern, which makes maintenance of data on client less clumsy.

## Slide 6: SANKEY LEARNINGS
Architectural Walkthrough – Any critical architectural decisions should not only be documented, but also be discussed thoroughly in a dedicated meeting and signed off.
Sign Off – Any critical deliverables to be pushed for sign off.
Communication - Communication / Delivery can be facilitated more using tools like Symphony.
Integration – Sprint deliverables can go more hand in hand by working collectively over call / screen share for smooth integration.
UAT – UAT period can be reduced if the QA Team can share their set of test cases beforehand with Sankey.

## Slide 7
THANK YOU!